## Sheet1
M/O |  | Generic requirements |  | Mandatory at
|  |  | Responsible | M0 | M1 | M2 | M3 | M4 | M5 | Comments
Project type
Requirements for all projects - project documentation
M | All | Project proposal | PO | X
M | All | Business case | PO | X | X | X | X
M | All | Project assignment | PO, PM |  | X | X | X
M | All | Stakeholder analysis/communication/training plan | PM |  |  | X | X
M | All | Plan for handover | PM |  |  | X | X | X
M | All | Impact of changes on the organisation | PM |  | X | X | X
M | All | Benefits realisation plan | PO |  |  |  | X | X | X
M | All | Status report | PM
Requirements for all projects - tasks, confirmations and sign-offs
M | All | Project Arena recommendation | PO | X | X
M | All | Commitment of all resources | PM |  | X | X | X
M | All | Sign-off from controller | PM |  | X |  | X
M | All | Process owner sign-off | PM |  | X |  | X
M | All | Lessons learned (Experience transfer) | PM |  |  | X | X | X | X
M | All | QA | PM |  | X | X | X | X
M | All | Enterprise Architecture | PM |  | X | X | X | X
M | All | Project closure | PM | [5 empty] | X
Requirements for projects with procurement
M | Proc. | Procurement plan | PM |  |  | X | X
M | Proc. | Project CSR plan | PM |  |  | X | X
M | Proc. | Request for proposal (RFP) and Procurement | PM |  |  |  | X
M | Proc. | Requisition to supplier | PM |  |  |  | X
M | Proc. | Contract with supplier | PM |  |  |  |  | X
Requirements for Scrum projects
M | Scrum | Product backlog | PO |  | X | X |  | X
M | Scrum | Release plan | PM |  |  | X
Requirements for IT projects
O | IT | Result from market survey | PM |  | X
O | IT | Result from market assessment | PM |  | X
O | IT | Alternative solutions | PM |  | X | X
M | IT | Business impact analysis | PO |  | X
M | IT | Requirement specification | PM |  |  | X |  | X
O | IT | As-Is work processes and related systems | PM |  |  | X
O | IT | To-Be work processes and related systems | PM |  |  | X |  | X
O | IT | Gap analyses | PM |  |  | X
M | IT | Information Risk Assessment | PM |  |  | X
O | IT | Plan for usability evaluation | PM |  |  | X
M | IT | Test plans | PM |  |  | X | X | X
M | IT | Plan for operational verification | PM |  |  | X | X | X
M | IT | Key controls | PM |  |  | X |  | X
M | IT | System context description | PM |  |  |  | X
M | IT | Sourcing decision document | PM |  |  |  | X
M | IT | Recommended solution | PM |  |  |  | X
M | IT | Functional specification | PM |  |  |  |  | X
O | IT | Plan for data migration | PM |  |  |  |  | X
Requirements for Facility management projects
M | FM | Requirement specification | PM |  |  | X
M | FM | Recommended solution | PM |  |  | X | X
M | FM | HSE plan | PM |  |  |  | X
Requirements for Organisational development projects
O | OU | Doc 1 | PM
O | OU | Doc 2 | PM