Table of contents

1	Summary of the project assignment	1

1.1	Validity	2

1.2	Purpose of the project assignment	2

1.3	Background	2

1.4	Business case	2

2	Goals, objectives and scope	3

Technique	3

2.1	Project goals (effects to be achieved)	4

2.2	Project objectives (results to be achieved)	4

2.3	Project scope	4

2.4	Project scope does not include	5

3	Prerequisites	5

3.1	Constraints	5

3.2	Assumptions	5

3.3	Health, Safety and Environment (HSE)	6

3.4	Corporate Social Responsibility (CSR)	6

3.5	Steering parameters	7

3.6	Interfaces and dependencies to other projects	8

3.7	Governing documents	8

4	Project plan	8

4.1	Milestone plan	8

4.1.1	Plan for budget freeze	8

4.2	Cross-functional projects etc. (if applicable)	8

4.2.1	Milestone plan for cross-functional projects etc (if applicable)	8

5	Project cost and financing	9

5.1	Project cost	9

5.2	Planned Target Estimate (PTE)	10

5.3	Project financing	10

6	Project risk	10

6.1	Project organisation	10

7	Project owner’s responsibilities	11

8	Change control	11

8.1	Change log (optional)	12

Summary of the project assignment

The project assignment is based on the Capital Value Process (CVP).

All chapters in the project assignment are mandatory.

Validity

This project assignment is valid up until the next decision gate, which is DGx.

This project assignment will be updated at each Decision gate. See further description in chapter 9.

Purpose of the project assignment

The project assignment defines the tasks given to the project manager by the project owner and is a formal delivery agreement between the project owner and the project manager/project manager. The purpose of the Project assignment is to:

- Define the task assigned to the project manager.

- Ensure that the assignment is clearly defined, understood and accepted by all parties.

- Clearly define the responsibilities of all parties.

- Delegate the necessary authority to the project manager.

The following roles apply to the project:

| Role | Name | Unit |
| --- | --- | --- |
| Project owner | <Project owner name> | <Business unit> |
| Project manager | <Project manager name> | <Project manager unit> |

Background

A short description of why the project was started.

What are the benefits for the business (e.g. problem description as a background for business needs and input on benefits from business case if possible)? What is the background and decisions made in the project owner’s organisation for this project? Refer to business strategies, project owner projects and key performance indicators for the project owner if possible.

Please refer to the priority or criticality for the project if known (from both project owner and project manager).

Business case

The project owner is responsible for the business case. The business case must be prepared before DG1 and updated before DG2 and DG3 and as needed.

The Project owner should continuously ask him-/herself:

- Is this the right thing to do?

- Is this within my authorities?

- Can I justify spending all this money on this?

- What is the Return On Investment (ROI)?

The project assignment should include a business case summary with a conclusion and/or print screen of summary + link to document.

The business case should address qualitative and quantitative costs and benefits. The costs must be identical to the estimated project costs given in Chapter 5.1 (Project Cost). The business case also requires an estimate for operational/yearly costs.

The project manager should estimate cost. The project owner should estimate benefits for the project outcome.

Benefits should be described and quantified using the same time horizon as for the costs. If quantification is not possible for some of the benefits, then these should be described qualitatively.

Business case summary: Copy/Paste the worksheet called summary from the business case spread sheet.

Detailed business case will be found in the Project manual.

Goals, objectives and scope

- Technique

The technique for identification of goals and objectives is based on the problem description. The technique has three steps:

1. Problem description:

Describe the problem from a business point of view. Try to be as specific as possible - what is the problem, which users are experiencing it? Use two levels in the problem description if there are several problems to be solved and a sensible way of grouping them. A short description of the problem area might be added, but often just a heading will suffice.

2. Identify project goals

Project goals represent what the business wants to achieve by solving the problem. This will constitute the benefit side of a business case. The project owner or the project owner representative should be involved in this step. Try to find SMART (see below) goals that may be used in a business case.

3. Identify project objectives

Project objectives represent what the project should produce or achieve to solve the problems: a new system, improved work processes or any other project result. The objectives are the cost drivers in the business case.

SMART goals

S = Specific/stretching: clear, unambiguous, straightforward, understandable and challenging.

M = Measurable: quantity, quality, time, and money.

A = Achievable: challenging, but within the reach of a competent and committed team.

R = Relevant: relevant to the goals of the organization so that the goal of the team is aligned to the corporate goals.

T = Time-framed: to be completed within an agreed timescale.

Example - The project goals (effects to be achieved) are:

  - Reduced net effort on pricing and invoicing from 3 to 1.5 man-years per year after implementation of new system solution and revised work processes.

  - To reduce the potential running expenses by 2.6 million per year.

  - To remove 90% of today's manual registration work.

Project goals (effects to be achieved)

"The goal is where we want to be. The objectives are the steps needed to get there."

A project goal refers to the expected achieved effects after the project is completed. Business participants in the pre-study must have a key responsibility in defining goals. Documentation and communication of these goals will increase the understanding of what the project should help the business to achieve. Goals should be concrete, unambiguous and measurable and should if possible, include a quantification of the improvement. Note that goals are an important input to the business case.

Project objectives (results to be achieved)

Project Objectives refer to the deliverables that the project is to hand over to the project owner and the users (for instance project deliverables at DG4). The project deliverables are the results that must be obtained in order to achieve the desired Project Goals (effects).

Objectives should express results for (1) 'physical' deliverables such as IT systems, hardware or documentation, (2) intended changes in organisation and work processes, and (3) results related to personnel (training etc.). It is a common mistake to over-emphasize 'physical' results and not to include objectives for organisation, processes and personnel. This can typically lead to an imbalance in project focus, and subsequently that the line organisation will not achieve the desired effects.

Objectives should be concrete, unambiguous and measurable. If this is done properly, it will be possible to determine whether an objective has been reached or not. Note also that objectives can be further detailed in the scope section.

Example - The project objectives (results to be achieved) are:

  - IT system support established for pricing and invoicing of product areas A and B.

  - Work processes for pricing and invoicing improved, aligned with new system and documented.

  - IT system and revised work processes implemented for business units X and Y.

  - Invoicing personnel trained in new system and revised work processes.

Project scope

The scope of the project refers to the project deliverables in more detail. Based on the objectives, the scope of the project is detailed.

The scope section will normally repeat/reformulate project objectives and add additional detail that improves understanding of what results the project will deliver and to which business/process areas. This section should be concrete, unambiguous and consistent with the project objectives.

<Project objective 1>

  - <Additional details >

  - <Additional details >

  - etc.

<Project objective 2>

  - <Additional details >

  - <Additional details >

  - etc.

Example - Establish IT system support for pricing and invoicing of product areas A and B including:

  - Adapt and implement the chosen IT-solution.

  - Integrate with existing project owner & order management system.

  - Transfer necessary data from current spread sheets used for pricing and invoicing.

  - User training.

Project scope does not include

What is not included in project scope should be described. Defining what is not included will ensure an improved and more consistent understanding of project scope. Any potential overlap in scope with other on-going projects should be addressed and resolved, see chapter 3.5 Interfaces and dependencies to other projects.

Example - The project scope does not include:

  - The project will not address project owner & order management, since this will be handled unchanged by existing system and processes.

  - The line management should cover training cost for the user.

  - The project is not responsible for realizing the benefits indicated for each delivery. This is the responsibility of the line organization.

Prerequisites

Constraints

A constraint is an applicable restriction that will affect the execution of the project. It is important to identify, assess and document all constraints that apply to the project. Constraints can be related to organisation, governing documents, law, resources, competence, technology, time schedule, budgets, budget years and so forth.

Constraints are identified and then managed.

Example - Constraints:

  - The specification and development of IT solutions cannot be started before the work processes are described.

  - Development platform – Microsoft .Net 3.5

Assumptions

Assumptions are factors that for planning purposes are considered to be true, real, or certain. It is important to document all underlying assumptions made when establishing goals, plans, budgets, business case assessment etc.

Assumptions are identified and then managed.

Example - Assumptions:

  - The line/business organisation have settled unresolved issues regarding product area A, and have the required competence to start definition of business requirements for pricing and invoicing for this product area, within <given date>.

  - The line/business organisation has resolved pricing data quality issues, before data transfer to new IT system is to be carried out.

Health, Safety and Environment (HSE)

It is important that the project owner and the project manager are aware of the requirements listed in our governing documents, and that the project is planned up front to include this. The project owner and project manager are responsible for that the projects are delivered according to HSE requirements.

Special challenges for this project assignment within health, safety and environment are:

Example

- The companyworks actively to develop common goals, attitudes and behaviour in HSE areas, and is a driving force for continuous improvements.

- HSE criteria will be applied when evaluating and selecting suppliers and/or goods and services.

- HSE requirements for products and services will be incorporated in this assignment.

- The assignment specific challenges within health and the working environment, environment, safety, security and emergency preparedness (HSE) shall be discussed and visualised in the specific assignment.

- The project owner is responsible for ensuring that HSE challenges are evaluated and incorporated in the specific assignment as applicable.

Other HSE examples could be:

- Noise

- Ergonomics

- Office locations

- Energy consumption

Corporate Social Responsibility (CSR)

All projects will be delivered according to CSR requirements.

It is important that the project owner and the project manager are aware of the requirements listed in our governing documents, and that the project is planned up front to include this. The project owner and project manager are responsible for that the projects are delivered according to CSR requirements.

Special challenges for this project assignment within CSR are:

Example

- The company works actively to develop common goals, attitudes and behaviour in CSR areas, and is a driving force for continuous improvements.

- CSR criteria will be applied when evaluating and selecting suppliers and/or goods and services.

- CSR requirements for products and services will be incorporated in this assignment.

- The assignment specific challenges within Corporate Social Responsibility (CSR) shall be discussed and visualised in the specific assignment.

- The project owner is responsible for ensuring that CSR challenges are evaluated and incorporated in the specific assignment as applicable.

Steering parameters

The project manager must agree on steering parameters with the project owner. The purpose is to give the project manager important steering information, i.e. information on what is important for the project owner.

The steering parameters must be given a weight. Weighting is used in order to indicate priority and importance of one parameter in relation to another. There should always be one steering parameter with a higher weight than the others. This is to give the project real guidance as to what is most important for the project owner.

Evaluation criteria for each of the parameters could be stated. The project owner is responsible for the actual weighting of the parameters. Typical steering parameters are scope, time, cost and quality. See the table below for examples. It is up to the project owner of the individual project to decide how many steering parameters to register but more than 6 is not recommended.

The steering parameters may change during the project life cycle. Guidelines for when steering parameters may be changed should be made. The project owner and the project manager must approve all changes to the steering parameters. Typical situations that justify changes in steering parameters evaluation criteria are conditions that are beyond the project's control, for instance changes in scope because of changed requests from the project owner/user. The steering parameters evaluation criteria could mainly be changed in four ways:

- Changes in a parameter's baseline, for instance due to extended scope (e.g. the budget is increased from 10 MNOK to 15 MNOK) must be allowed to happen continuously.

- Changes in a parameter's evaluation criteria should not happen often. To be considered at each "Decision gate".

- Changes in priorities between the parameters priorities/weighting should not happen often. To be considered at each "Decision gate".

- Adding or removing parameters should not happen often. To be considered at each "Decision gate".

Note! For larger projects it may be a good idea to agree on steering parameters for each DG and that will apply until the next DG, this in order to get feedback more frequently. 

Steering parameters, an example by use of weights and evaluation criteria (optional):

| Weight | Steering parameters | Evaluation criteria |
| --- | --- | --- |
| 30% | Cost | No deviations from the cost estimate at DG3. |
| 20% | Time | No deviation from agreed delivery date is accepted |
| 15% | Quality of product | No critical mistakes |
| 15% | Availability of project manager for project owner and users | Be present in the project owner's premises 3 days a week |
| 10% | Minimal rotation of personnel in the project | The project manager should be the same person throughout the project. Among the rest of the participants there should be 80% stability. |
| 10% | Health, Safety and Environment | The project manager must ensure good working conditions and HSE for all participants in the project. |

Interfaces and dependencies to other projects

Any potential interfaces and dependencies with other on-going projects should be addressed and resolved. Any potential overlap in scope with other on-going projects should also be addressed and resolved. It is important to clarify what the dependencies to other project consist of. This should be described in brief for each of the projects.

Example - Interfaces and dependencies to other projects:

  - <project name>, <business unit>, <project manager>, <description>

Governing documents

Applicable governing documents should be listed. It is the project manager’s responsibility to ensure that the project is in line with all relevant governing documents.

Project plan

A good plan is one that stakeholders find sufficiently reliable so they can use it as the basis for making decisions. Early in the project this plan will be coarse and tentative. Later in the project, to remain useful for decision-making, this plan will need to be more precise.

Milestone plan

A milestone plan for the project should be developed at a high level. The milestone plan should include a timeline and the formal Decision Gates for the total project.

| DG | Date | Description |
| --- | --- | --- |
| DG1 |  |  |
| DG2 |  |  |
| DG3 |  |  |
| Dg4 |  |  |
| DG5 |  |  |

Plan for budget freeze

The project must ensure that the budget freeze (normally at DG3) is planned to fit the project’s needs. This will probably mean that the budget will be frozen at one of the DG3s, but this needs to be decided according to the timeline of the project.

This plan should be included in the Project assignment. Any changes in this plan should be documented in the next Project assignment.

Cross-functional projects etc. (if applicable)

The following applies to cross-functional projects and projects comprising more than one delivery or sub-project

Milestone plan for cross-functional projects etc (if applicable)

High level milestone plan:

| DG | Date | Description |
| --- | --- | --- |
| DG1 |  | Common for all sub-deliveries |
| DG2 |  | One or more project DG2’s aligned with the need for QC. |
| DG3 |  | This should be equal to the time for DG3 of the last sub-delivery. At this point the time and cost estimates will be locked to form the basis for measuring performance. |
| DG4 |  | Time should be equal to Approval point of the last sub-delivery |
| DG5 |  | Common for all sub-deliveries |

E. g. the following milestones apply for the sub-deliveries:

Delivery A:

- DG2

- DG3

- DG4

Delivery B etc.

Project cost and financing

This chapter should include information regarding project cost as well as project financing.

Project cost

This chapter should include the estimated project cost for the total project, including a higher rate of accuracy. Please note that the estimated project cost should always be presented together with the agreed accuracy, preferably as a range.

The accuracy for the total delivery should be within the following frames:

- At Decision Gate 1 (DG1) +/- 60%

- At Decision Gate 2 (DG2) +/- 40%

- At Decision Gate 3 (DG3) +/- 30%

It is important to be specific on the accuracy of estimates provided. At pre-study stage, the accuracy of estimates for the entire project can typically range from 50% and upwards to several hundred per cent - depending on the characteristics of the project. This section should preferably provide project estimates/budgets as a range to specifically show the accuracy. The numbers must be accompanied by comments, which clearly indicate accuracies and any key assumptions that have been made. Be careful not to make unrealistic assumptions (for example to assume that all resources will have the required competence).

Similarly, the estimates for the yearly/operational costs (e.g. hardware maintenance cost, licences, network maintenance cost, and man-hours for maintenance) may have a high accuracy and should be treated as for project costs.

It is strongly recommended to perform a quality control of estimates before any estimates/budgets are communicated to project owner or steering committee.

This document will be updated at each decision gate until DG4.

Note that cost estimates at DG3 should be considered as final cost budget for the project.

It is important that the project estimate covers the scope of the project assignment – i.e. the work that the project manager takes responsibility for delivering. If parts of scope are delivered by a project owner resource, this should still be included in the project estimate.

Detailed project cost will be found in the Project manual.

Planned Target Estimate (PTE)

Project owner must approve the planned target estimate (PTE), and at DG3 this estimate will represent the project baseline. The project baseline will be frozen at DG3.

| Decision Gate | PTE (1000 NOK) | Comment (if relevant) |
| --- | --- | --- |
| DG1 |  |  |
| DG2 |  |  |
| DG3 |  |  |
| DG4 |  |  |
| DG5 |  |  |

Project financing

This chapter should include information regarding the financing organisation and which cost center is financing the project.

| Financed by project owner/service | Cost center | % |
| --- | --- | --- |

The financing information is used when establishing SAP PS project settlement rules for the project.

Project risk

This section should describe the specific risks that have been identified for the project at a high level. The Project assignment will only be updated at each decision gate. Risk management at a more detailed level should be handled the Project manual or the Project Execution Plan.

Risk is an uncertain event or condition that, if occurs, has a positive or negative effect. Risks can be related to time, cost, quality, scope, project execution, project organisation, line organisation, competencies, technology etc.

To improve focus, this should be limited to the key risks that are specific to this project - maximum 10. Each risk element should be described with a short description, probability, consequence if it occurs and mitigation measures. Use the tabular format and the probability/consequence diagram provided by the best practice. This diagram will be an important tool in the subsequent risk management of the project.
Project organisation and stakeholders

Project organisation

This section should provide a description (e.g. a chart) of the recommended project organisation including the steering functions. The recommended project owner and project manager should be named. The chart and description should clearly indicate any sub-projects and their responsibilities - for example if deliveries are managed as a sub-project of the total project.

Project roles and staffing plan can be described. Every project should include at least two roles:

- Project owner - is financially and commercially responsible

- Project manager - is responsible for meeting the agreed steering parameters

Note that one person can fill more than one role.

The following resources are committed from the project owner organisation:

| Name | Role | Unit | % | From-To date | Comments |
| --- | --- | --- | --- | --- | --- |

The following resources are committed from the project manager:

| Name | Role | Unit | % | From-To date | Comments |
| --- | --- | --- | --- | --- | --- |

Other stakeholders:

It is important to make a proper identification and analysis of stakeholders and their interest/involvement in the project. Insufficient stakeholder analysis is a frequent reason for various problems such as scope changes in project execution. A proper stakeholder analysis will also be an important input to project organisation (participation in steering committee, QA groups etc.) and to the communication plan.

If the project is dependent upon deliveries from external suppliers or sub-contractors this should also be described in the section for other stakeholders. This will usually be relevant at DG3.

Other stakeholders:

| Name | Role | Unit | % | From-To date | Comments |
| --- | --- | --- | --- | --- | --- |

It is up to each project to decide which roles are necessary and how detailed the responsibility descriptions should be.

Project owner’s responsibilities

The project manager must deliver according to the agreements of this document. To enable the project manager, the project owner has to the take the responsibility of the tasks described in this section. It is recommended that someone from the project owner side estimates the effort needed to deliver the agreed tasks.

| Deliverable | Project owner’s responsibilities | Other agreements |
| --- | --- | --- |

Change control

Requests for changes must be addressed written, and the project manager must evaluate the consequences of the change with respect to cost, time, quality etc. Detailed routines for Scope Change control will be found in the Project manual or the Project Execution Plan.

The project manager has the authority to approve changes for <%/MNOK> of the approved budget.

The accepted changes should only have consequences within the limits that the project manger has been given the authority for. The project owner will be informed about the project managers accepted changes if needed. The project manager can not accept changes that will have consequences for time and quality without discussing with the project owner.

Changes of the project assignment

The project assignment will be updated at every decision gate. The project manager, together with the project owner, will be responsible for revising and updating this document.

It is important to archive the document for each decision gate. Use the correct document name from the beginning if possible. The document should be named after the following standard:

- <Project name> Project assignment <Decision gate>
E.g. TickerR4 Project assignment DG2

Change log (optional)

Provide a brief description of changes in the document from last DG.

| Date | Chapter | Description | Comments/link |
| --- | --- | --- | --- |