| No. | Control questions | Comments | Status |
| --- | --- | --- | --- |
| 1-20 contain questions regarding the project plan |  |  |  |
| 1 | Have you configured your work model? | Are the project deliverables defined? Clearly defined deliverables form the basis for the project follow-up. Are the deliverables defined clearly with regards to: - What have been included in the delivery - What has not been included - Time of delivery - Sub-deliverables, including deliverables from sub-vendors - Acceptance/approval - Documentation (content, quality) - Routines and terms regarding - Training - Installation - Conversion - Go-live |  |
| 2 | Have you identified and described the main activities? |  |  |
| 3 | Should the project be split into sub-projects? | Must be considered for projects with high complexity and high risk. For example projects with many stakeholders. The project plan must cover all sub-projects. |  |
| 4 | Have you clearly defined the milestones (Mx) to enable necessary decisions? | Necessary decision basis must be provided prior to the milestones (Mx). |  |
| 5 | Have you added enough calendar time in connection to the milestones (Mx)? | Decisions often take time, even though there are not spent many man-hours on the activity. Try to avoid frustrations when the project continues without the necessary decisions. |  |
| 6 | Is the duration of the project too long? | Try to avoid projects lasting more than 7 months (after M1). It is important for the customer to have quick results, and the number of change requests decrease with quick delivery. |  |
| 7 | Does the project plan reflect external frame conditions? | The project manager must get an overview of dependencies towards other projects, and other conditions affecting the project to make sure they are coordinated in a good manner. |  |
| 8 | Is this project dependent on deliverables from other projects? |  |  |
| 9 | Will delays in this project affect other projects or external activities? |  |  |
| 10 | Is this project part of a bigger project or program? | It is important to clearly define the deliverables of all projects and sub-projects. |  |
| 11 | Does this project have interfaces to other systems? | Interfaces to other systems must be coordinated. Usually this requires resources on both sides of the interfaces. |  |
| 12 | Have you added uncertainty to the plan? | Have known risk factors and other uncertainty been considered? Discuss the amount of uncertainty to be added to the project plan with your asset owner. |  |
| 13 | Have you allocated time for change requests, risk management, reporting and follow-up and other project administration? |  |  |
| 14 | Have you planned for operational verification? | The length of the operational verification period must be planned, and acceptance criteria must be agreed upon. |  |
| 15 | Have you produced a Gantt chart? |  |  |
| 16 | Has the project plan been evaluated by the quality control manager and approved by the steering committee? |  |  |
| 17 | Have you reviewed the operations handover checklists to ensure you project activities cover the requirements from operations? |  |  |
| 18 | Have you planned for the archiving activity, which is required during handover phase before M5? |  |  |
| 19-37 contains questions regarding detailed plans for the next phase. |  |  |  |
| 21 | Does the project plan reflect correct level of details regarding time writing and follow-up? | Time writing must be in accordance with the main activities/activities in the project plan. Activities are the lowest level for time writing. |  |
| 22 | Have you specified all necessary deliverables and configured your work model? | Check your work model. Be conscious regarding the level of details for the activities. Maintain a reasonable level to obtain necessary control of the project. You must document removal of mandatory deliverables. |  |
| 23 | Have you described the activities? | The descriptions must be clear and start dates/stop dates, results and resource requirements must be included. |  |
| 24 | Have you included slack in the project plan? | Do not plan for 100% efficiency. Do not plan for overtime. Include uncertainty in your estimates. |  |
| 25 | Have you defined the dependencies between the activities? | Evaluate critically the dependencies between the activities and make sure the activities are started in the most efficient order. |  |
| 26 | Have you appointed a responsible person for each activity? | Do not emphasize detailed resource allocation but underline the areas of responsibility for all project members. |  |
| 27 | Can some activities be run in parallel? |  |  |
| 28 | Have you included recurring activities for each phase in the project plan? | Remember recurring activities such as SC meetings, core team meetings etc. |  |
| 29 | Have you planned time for quality management activities? | Quality management takes time! Make sure you plan for this. |  |
| 30 | Have you planned time for corrections? | It is often necessary to make corrections after milestones, quality control activities etc. |  |
| 31 | Have you planned enough time for testing? | Test management and testing take time. Always plan for corrections/changes/retesting after test. |  |
| 32 | Have you planned enough time for phase-out of existing systems? | Normally existing systems run in parallel with the new system to test if both systems give the same results. |  |
| 33 | Have you planned enough time for project administration? | Project administration takes relatively much time. Allocate minimum 20% of total time to this. The hours are spent on follow-up, change management, status reporting and project meetings. |  |
| 34 | Have you allocated enough time for team building? | Allocate time for team building and other social events. |  |
| 35 | Have you made plans for training of project team members? |  |  |
| 36 | Have you planned enough time for transfer of competence when replacing team members? |  |  |
| 37 | Has the project plan been evaluated by the quality control manager and approved by the steering committee? |  |  |
| 38 | Does the project plan consider all frame conditions? | Remember that the project manager is free to adjust the plan and make own priorities within a phase, as long as the steering parameters have not been exceeded. Make revisions and get new approval for major changes from the steering committee if necessary. |  |