## A
RACI-MATRIX for <project>
Superior level
Roles | Project manager | Project group. | User responsible | Consultants | Steering committee
Project planning | RA | U | A |  | D
Budget | RA |  |  |  | D
Development | R | C |  | A | I
Testing | I | RA | A | A | I
Training | C | A | R | A | I
Detailed level
Resources | Peter | Diana | Christine | John | Dan
Revised project plan | RA | D | C | C | A
Plan training site A | C | A | A | I | R
Plan training site B | C | A | A | I | RA
Develop module A | I |  |  |  | RA
Develop module B | I | I | C | C | A
Testing module A | I | I | A | A | R
Testing module B | I |  | A | A | R
Perform training site A | C | A | I | A | I
Perform training site B | C | A | A | I | I
R - Responsible
A - Accountable
C - Consulted
I - Informed
D - Decision