## Risk assessment
Risk check-list |  |  | Relevance | Probability | Consequence | Risk points
|  |  | 0-1 | 1-3 | 1-3 | Probability
|  |  | 0 = Not relevant | 1 = Slight | 1 = Trivial | *
ID | Risk area | Control questions | 1 = Focused | 3 = High | 3 = Seriously | Consequence
1 | Dependencies | Are there any dependencies regarding resources?
2 |  | Are there any dependencies regarding competence?
3 |  | Are there any dependencies regarding user involvement?
4 |  | Are there any dependencies regarding steering committee - commitment, decision willingness, involvement?
5 |  | Are there any dependencies regarding other projects or tasks?
6 |  | Are there any dependencies regarding suppliers?
7 |  | Are there any dependencies regarding contract negotiation?
8 | External conditions, constraints | Are there issues outside of the project which may influence the project to a great extent?
9 |  | Are there uncertainties regarding external conditions/constraints?
10 | Businesslike | Are the delivery dates invariable/fixed?
11 |  | Are there any consequences if the project is delayed?
12 |  | Are the deliverables very important for the customer? (NB! This can strike both ways - there may be less risk that a very important project is terminated, but if the project is delayed it may have greater consequences for the business).
13 |  | Is the area of operation unstable (organizational changes, change of business goals, scope etc)?
14 | Project size and scope | Are the project objectives unclear?
15 |  | Are the requested deliverables defined unclearly?
16 |  | Is the size of the project a risk?
17 |  | Is the time horizon for the project causing a risk?
18 |  | Is the number of locations for the deliverables to be implemented causing risks?
19 |  | Are there many activities that are mutually dependent? For instance - is this a very compound deliverable?
20 |  | Are there many subcontractors involved?
21 | Organisation | Has the project manager insufficient experience from other projects of same size?
22 |  | Has the project manager insufficient experience from the business area?
23 |  | Has the project group insufficient experience and competence?
24 |  | Will the project group be placed at different locations?
25 |  | Are there many members of the project group?
26 |  | Are members of the project group assigned to the project part-time?
27 |  | Do project members have different objectives or different background?
28 |  | Are there any personal conflicts?
29 |  | Are project members unfamiliar with the project model and/or work model to be used?
30 | Customer | Does the customer have unrealistic expectations?
31 |  | Will the asset owner be appointed late in the process?
32 |  | Are the expectations uncoordinated, not understood or not accepted?
33 |  | Does the customer show unwillingness to take ownership?
34 |  | Is the customer unwilling to take risks?
35 | User | Are there many different user groups are involved?
36 |  | Do the users disagree or are there many stakeholders with various requirements and wishes?
37 |  | Is the management in the user environment unsufficiently involved or committed?
38 |  | Will the project group be separated from the users?
39 |  | Do the users lack previous experience with this kind of projects?
40 |  | Will the project cause big changes for the user organisation and routines?
41 | Commitment | Are the users absent whenever their presence is required?
42 |  | Do the customer and/or users hesitate to respond to requests within the given deadlines?
43 |  | Has the project problems with the progress due to lack of commitment from the user/customer side?
44 | Decision-making | Are the asset owner, steering committee and service provider unable to make decisions?
45 |  | Does it take a long time from project asks for a decision to be made until it is actually made?
46 |  | Does the project have problem with the continuity due to decisions not being made at the agreed times?
47 | Planning | Can project plans still be changed or not approved?
48 |  | Do you still lack confirmation regarding when all necessary resources will be made available?
49 |  | Are user resources unavailable?
50 |  | Are contracts with subcontractor unsigned?
51 |  | Are there too little slack to the project plan or estimates?
52 |  | Are the routines for quality assurance not good enough?
53 |  | Have routines for change management not been established?
54 |  | Are the estimates uncertainties unclear or unknown?
82 | Information | Is the communication plan insufficient?
83 |  | Are any stakeholders reluctant to receive information or hard to get in contact with?
84 |  | Will any stakeholders be left out from the information flow?
55 | Other projects | Is the project dependent upon deliverables from other projects?
56 |  | Are other projects dependent upon deliverables from this project?
57 |  | Is this project dependent upon the completion of other projects?
58 | Technical | Are there unknown technical issues?
59 |  | Is the technical environment unknown (new technology)?
60 |  | Are the deliverables complex in nature?
61 |  | Are the deliverables based on in-house development (as opposed to off-the shelf or standard solutions)?
62 |  | Are there particular critical requirements with respect to security and robustness?
63 |  | Is there great focus on technology as problem solver?
64 |  | Are there insufficient reuse and use of standards?
65 |  | Is the implementation time too long?
66 |  | Is the requirement specification unclear or inadequate?
67 | Testing and acceptance | Are the users unsufficiently responsible for defining tests- and acceptance criteria?
68 |  | Are the users unsufficiently involved in testing?
69 | Implementation | Is the infrastructure (hardware, network etc.) not in use and unknown to the project participants?
70 |  | Are there many interfaces to other systems?
71 |  | Are the users or IS/IT personnel unavailable for training?
72 |  | Are there any difficulties involved in replacing existing solutions?
73 | Operation and maintenance | Have production responsible and system responsible not been appointed?
74 |  | Has the solution been unsufficiently discussed with those who will be responsible for operation and maintenance?
75 |  | Is the system's availability critical?
76 |  | Does error-correction take long time?
77 |  | Are there any short-term maintenance contracts?
78 |  | Are legal and contractual aspects unclear regarding maintenance?
79 |  | Has the contractor and the customer different objectives?
80 |  | Has the contractor insufficient solidity?
81 |  | Is the contractor unwilling to share risk?
82 | Other risks
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
| Sum Risk points |  |  |  |  | 0

## Presentation
ID | Risk
1
2
3
4
5
6
7
8
4
3
2
5
6
7
8
1